|  |  |
| --- | --- |
|  | On Time |
|  | Lately |
|  | Early |
|  | Unfinished |

|  |  |
| --- | --- |
| **Project Name:** | **LEARNING ENGLISH TOGETHER** |
| **Module Name:** | Sprint 2 |
| **Development Team:** | Group4 |
| **Start Date:** | 18/2/2024 |
| **End Date:** | 8/3/2024 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | | | | |  | | | | | | | | | | | | | | | | | | | | | | | | | | | | |
| **No.** | **Member Name** | | **Estimate** | **Actual** |
| 1 | Nhan | Trần Phúc Nhân | 61 | 65 |
| 2 | Tuan | Huỳnh Anh Tuấn | 67 | 70 |
| 3 | Vu | Trần Thanh Vũ | 65 | 69 |
| 4 | Thi | Trương Thị Mai Thi | 66 | 73 |
| **Total** | | | 259 | 277 |
| **SPRINT 2 REPORT** | **Conponent** | **Task Name** | **Resposible Member** | **Actual** | **18-Frb-24** | **19-Feb-24** | **20-Feb-24** | **21-Feb-24** | **22-Feb-24** | **23-Feb-24** | **24-Feb-24** | **25-Feb-24** | **26-Feb-24** | **27-Feb-24** | **28-Feb-24** | **29-Feb-24** | **01-Mar-24** | **02-Mar-24** | **03-Mar-24** | **04-Mar-24** | **05-Mar-24** | **06-Mar-24** | **07-Mar-24** | **08-Mar-24** | **09-Mar-24** | **10-Mar-24** | **11-Mar-24** | **12-Mar-24** | **13-Mar-24** | **14-May-24** | **15-May-24** | **16-May-24** | **17-May-24** |
|  | **Sprint Plan Meeting** | | All member | 6 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Create Sprint Backlog for Sprint 2** | | Nhan | 6 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Create Test Plan document for Sprint 2** | | Nhan | 8 | 8 | 6 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Design UI** | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI Find a helper | | Tuan | 8 | 8 | 6 | 3 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI Support for user | | Vu | 8 | 8 | 6 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI Search user | | Thi | 8 | 8 | 5 | 3 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI Learn Vocabulary | | Tuan | 10 | 10 | 10 | 10 | 10 | 8 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI Quiz | | Tuan | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI test case Find a helper | | Vu | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI test case Support for user | | Vu | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI test case Search user | | Thi | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI test case Learn Vocabulary | | Tuan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UI test case Quiz | | Nhan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Database** | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design database | | Thi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **Coding** | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Front-end) Find a helper | | Tuan, Nhan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Front-end) Support for user | | Vu | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Front-end) Search user | | Nhan | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Front-end) Learn Vocabulary | | Nhan | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 3 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Front-end) Quiz | | Tuan | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Back-end) Find a helper | | Vu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Back-end) Support for user | | Vu | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Back-end) Search user | | Thi | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Back-end) Learn Vocabulary | | Thi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (Back-end) Quiz | | Thi | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | **Testing and fix bug** | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Front-end) Find a helper | | Vu | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Front-end) Support for user | | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 1 | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Front-end) Search user | | Tuan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Front-end) Learn Vocabulary | | Vu | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Front-end) Quiz | | Tuan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Back-end) Find a helper | | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  |  |  |  |  |  |  |
|  | Design Test Case for (Back-end) Support for user | | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  |  |  |  |  |
|  | Design Test Case for (Back-end) Search user | | Tuan | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  |  |  |  |  |
|  | Design Test Case for (Back-end) Learn Vocabulary | | Ha | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 |  |  |  |  |  |  |  |
|  | Design Test Case for (Back-end) Quiz | | Tuan | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 |  |  |  |  |  |  |  |
|  | **Fix Bug & Release Sprint 2** | |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Implement test case | | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 4 |  |  |  |  |  |  |  |  |
|  | Fix bugs and report | | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 11 | 7 | 5 | 3 | 2 | 2 | 0 |
|  | Retest | | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 7 | 5 | 3 | 2 | 1 | 0 |
|  | Closing | | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |
|  |  |  | **TOTAL** | **259** | **251** | **238** | **225** | **217** | **207** | **196** | **184** | **174** | **162** | **150** | **138** | **132** | **123** | **110** | **99** | **89** | **80** | **71** | **61** | **53** | **45** | **27** | **22** | **16** | **12** | **8** | **6** | **5** | **0** |