## Product Backlog
Product Backlog
1 = High prio and 3 = Low prio
Id | Epics / Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Priority | Estimate (Hours) | Remarks/Comments/Additional info
PB01 | Register | User | Create an account | Save grocery | - Phone # in VN format, contains no alpha characters, minimum 10 digits - Full name and email address required - Email specified in standard format - Email must have @gmail.com and >=8 | 1 | 20
PB02 | login | User | Login existed account | use app | Account in database | 1 | 10
PB03 | Logout | User | Logout current account |  | Already login | 1 | 15
PB04 | Reset password | User | Reset forgotten password | Set new password | Confirm throught email/number phone | 1 | 10
PB05 | Create grocery list | User | Create specific grocery list | Save grocery for specific usage | List havent created yet | 1 | 15
PB06 | Add groceries to list | User | Add grocery to selected list | Add items to list | - items on list have quantity less than 9999999 - summary list less than budget of cycle | 1 | 10
PB07 | Remove groceries from list | User | Remove grocery from selected list | Remove unnescessary item from selected list | - item existed in list | 1 | 10
PB08 | Calculate money | User | See how much money each list/all list | Calculate money | - at least 1 list existed - list not empty | 1 | 5
PB09 | Memorize previous cycle | Stake holder | Remember user's last cycle | Improve user experiment | - a cycle should be 1 week or 1 month - selected by user | 1 | 20
PB10 | Suggest missing items | Stake holder | Suggest items | Improve user experiment | -Suggest items from previous cycles -Items're buy through at least 3 cycles | 1 | 20
PB11 | Budget for each cycle | User | See how much money spended last cycle |  | - cycle selected by user(1 month/1 week) - use app more than 1 cycle -have grocery in last cycle | 1 | 10
PB12 | Suggest recipes | User | Select recipe from grocery/list |  | -select list/groceries to see revelant recipes -recipe arcordding to religion/area/weather/allergies | 1 | 40
PB13 | Feedback | User | Feed back problem | Improve user experiment | Have account | 2 | 10
PB14 | bug report | User | Feed back bug | Improve user experiment | Have account | 2 | 10
PB15 | Login<=1s | Stake holder | user login less than 1s | Improve user experiment |  | 2 | 10
PB16 | Load <=1s | Stake holder | load funtion less than 1s | Improve user experiment |  | 3 | 10
PB17 | IOS | Stake holder | Can work on iphone |  | -Iphone more than 6 | 1 | 30
PB18 | Android | Stake holder | Can work on android |  | -Work on android OS devices | 1 | 30
PB19 | 2 Languages | Stake holder | Tranlate to 2 languages | Approach to more user | - Vietnamese -English | 1 | 10
PB20 | 200000 users login | Stake holder | 200.000 users at same time |  | -less than 1s -no lag | 2 | unknow

## Project Plan
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Staring | 2023-11-30 | 2023-12-07 | 2023-12-14 | 2023-12-21 | 2023-12-28 | 2024-01-04 | 2024-01-11 | 2024-01-18 | 2024-01-25 | 2024-02-01 | 2024-02-08 | 2024-02-15 | 2024-02-22 | 2024-02-29 | 2024-03-07 | 2024-03-14 | 2024-03-21 | PROJECT FINISH
Phase 1 | Planning
Create test plan
Design
Release document
Phase 2 |  |  |  |  | Sprint 1
Sprint 2
Sprint 3
Sprint 4
Phase 3 | [12 empty] | Test
Fix bugs

## Sprint 1 Backlog
[5 empty] | Make new estimate when move from PB to SB |  |  | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
Sprint Backlog |  |  | Add Owner when task is set to Ongoing | Update status during sprint
[6 empty] | After completed always = Estimate hours | Remaining work to be done.
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.1 | PB01 | Create database tables |  | Not started | 10 | 0 | 10
1.2 | PB01 | Create Login UI by Figma |  | Not started | 7 | 0 | 7
1.3 | PB01 | Create Homepage UI by Figma |  | Not started | 10 | 0 | 10
1.4 | PB01 | Create Resister UI by Figma |  | Not started | 5 | 0 | 5
1.5 | PB03 | Code && unit test |  | Not started | 30 | 0 | 30
1.6 | PB08 | Extract API |  | Not started | 5 | 0 | 5
1.7 | PB08 | Test |  | Not started | 10 | 0 | 10
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 77 | 0 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77 | 77
|  |  |  | Burn up |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Worked hours |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[6 empty] | Team member 1 | [16 empty] | 0
[6 empty] | Team member 2 | [16 empty] | 0
[6 empty] | Team member 3 | [16 empty] | 0
[6 empty] | Team member 4 | [16 empty] | 0
[6 empty] | Team member 5 | [16 empty] | 0
0
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint

## Sprint 1 Reports
Reports & Dashboards | This page is updated automatically when you update the numbers when a task is done in the Sprint 1 backlog sheet
Burn down Chart