## Plan
Project ABC |  | HUỲNH ANH TUẤN-27211200911
Earned Value Analysis - Phân tích EV
| Prepared By: | Nguyen Duc Man]
| Date: | 2024-04-07
[42]
| For Period: | Week 7
Summary:
Ghi kết luận của Dự án ở đây
BCWS
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Activity 1 | 5000 | 1000 | 2000 | 2000
1.2 | Activity 2 | 4200 |  | 500 | 800 | 900 | 2000
1.3 | Activity 3 | 4500 |  |  | 700 | 2000 | 1000 | 800
1.4 | Activity 4 | 3300 |  |  | 200 | 600 | 1000 | 1500
1.5 | Activity 5 | 3500 |  |  |  |  | 1000 | 700 | 1000 | 800
1.6 | Activity 6 | 7200 | [7 empty] | 700 | 2000 | 1500 | 2000 | 1000
0
0
0
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 27700 | 1000 | 2500 | 3700 | 3500 | 5000 | 3000 | 1000 | 1500 | 2000 | 1500 | 2000 | 1000
|  | Cumulative Planned Value (PV) | 1000 | 3500 | 7200 | 10700 | 15700 | 18700 | 19700 | 21200 | 23200 | 24700 | 26700 | 27700
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
|  | Cumulative Earned Value (EV) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
|  | Schedule Variance (SV = EV - PV) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
|  | Cost Performance Index (CPI = EV/AC) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
|  | Schedule Performance Index (SPI = EV/PV) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
|  | Estimated Cost at Completion (EAC) | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
Note on A21: ====== ID#AAAAIP56_S0 Vertex42 (2021-04-13 01:01:01) Work Breakdown Structure (WBS)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Activity 1 | 5000 | 20% | 50% | 100% | 100% | 100% | 100% | 100%
1.2 | Activity 2 | 4200 |  | 30% | 40% | 60% | 75% | 90% | 100%
1.3 | Activity 3 | 4500 |  |  | 25% | 40% | 50% | 100% | 100%
1.4 | Activity 4 | 3300 |  |  |  |  | 25% | 80% | 90%
1.5 | Activity 5 | 3500 | [5 empty] | 25% | 75%
1.6 | Activity 6 | 7200 | [6 empty] | 50%
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | ? | ? | ? | ? | ? | ? | ? | ?

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Activity 1 |  | Wk 1: 800; Wk 2: 500; Wk 3: 1500
1.2 | Activity 2 |  | Wk 2: 900; Wk 3: 700; Wk 4: 1200; Wk 5: 1700
1.3 | Activity 3 |  | Wk 3: 300; Wk 4: 300; Wk 5: 1250; Wk 6: 1500
1.4 | Activity 4 |  | Wk 3: 100; Wk 4: 500; Wk 5: 900; Wk 6: 700; Wk 7: 400
1.5 | Activity 5 |  | Wk 5: 400; Wk 6: 600; Wk 7: 500; Wk 8: 100
1.6 | Activity 6 |  | Wk 8: 700
- | -
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 800 | 1400 | 2600 | 2000 | 4250 | 2800 | 900 | 800 | ? | ? | ? | ?
Cumulative Actual Cost (AC) | bar: Wk 1 to Wk 12

## Bài 2
Bài số 2
Bạn có một dự án để xây dựng một hàng rào mới. Hàng rào
là bốn mặt. Mỗi bên sẽ mất một ngày để xây dựng và là
ngân sách với giá $ 10000 mỗi bên. Các bên được lên kế hoạch
hoàn thành hết phía này này đến phía khác. Hôm nay là kết thúc của ngày thứ ba.
Hãy tính PV, EV, AC, BAC, CV, CPI, SV, SPI, EAC, ETC, and VAC
| Task | Day 1 | Day 2 | Day 3 | Day 4 | Status end of Day 3 |  | Calculate (Formula) | Answer value | Explain the answer
| Buid side 1 | S -------------- F |  |  |  | Complete, spent $10 000 | PV
| Buid side 2 |  | S ---------- PF | ------- F |  | Complete, spent $12000 | EV
| Buid side 3 |  |  | PS ----- S --- PF |  | 50% done, spent $6000 | AC
| Buid side 4 |  |  |  | PS --------- PF | Not yet started | BAC
CV
|  | S: Start |  |  |  |  | CPI
|  | F finish |  |  |  |  | SPI
|  | PF - performance factor |  |  |  |  | SV
EAC
ETC
VAC

## Bai 3
Practice exercise on Earned Value Analysis (EVA):
Project Background:
You are managing a project to develop a new software tool. The project is scheduled to last for 12 months, with a budget at completion (BAC) of $600,000. The work is planned to be completed evenly over the project duration, meaning the planned value (PV) increases linearly over time.
Situation:
It's now the end of the 6th month, and you are conducting an earned value analysis to assess the project's health and performance. The following information is provided:
- Actual Cost (AC) to date: $350,000
- Earned Value (EV) to date: $300,000
Tasks:
1. Calculate the Planned Value (PV):
2. Calculate Schedule Variance (SV) and Schedule Performance Index (SPI):
3. Calculate Cost Variance (CV) and Cost Performance Index (CPI):
4. Estimate At Completion (EAC):
5. Estimate To Complete (ETC):
6. Variance At Completion (VAC):
7. Vẽ mô phỏng đồ thị dự án
8. Phát biểu kết luận dự án